|  |  |  |  |
| --- | --- | --- | --- |
| Deadline | Process/Activity | Outcome | Responsible |
| 7 March | * Lessons learned - ICCG | AAR | OCHA, ICCG |
| 22 August | * JIAF 2 Briefing | HNO | OCHA, ICCG |
| 29 August | * Updated baseline data, costing methodology | HNO/HRP | OCHA, ICCG |
| 1-5 September | * Agreements on the indicators and scope of the HNO | JIAF | IMOs, ICCG |
| 5 September | * [HCT] Seek HCT endorsement of HNO parameters - scope baseline data and HRP costing methodology | HNO/HRP | OCHA, ICCG |
| 13 September | * Secondary data review | SDR | IMOs, ICCG |
| 19 September | * Gender inputs to the process * Request other cross-cutting focal points to contribute | HNO/HRP | Cross-Cutting focal points/ICCG |
| 28 September | * Preliminary intersectoral needs analysis, PiN and severity estimates​ | HNO/HRP | IMOs, ICCG |
| 1 October | * Strategic and specific objectives. ​; prioritization -. Defined boundaries targeting | HRP | OCHA, ICCG, HCT |
| 11 October | * [HCT] Seek HCT endorsement on HRP parameters, Prioritization | HRP | OCHA |
| 12 October | * OCHA to share two templates with the ICCG – one for cluster narrative and the other for data (PiN, target and financial requirements) | HNO/HRP | OCHA |
| 22 October | * Clusters to share with OCHA inputs on cluster narrative, PiN, target and financial requirements | HNO/HRP | ICCG |
| 25 October | * OCHA to consolidate preliminary intersectoral targets and overall financial requirements | HRP | OCHA |
| 29 October | * Cluster defense | HRP | OCHA, ICCG |
| 31 October | * [HCT] Seek HCT endorsement on 2024 PiN, people targeted, financial requirements | HNO/HRP | OCHA |
| 2 November | * OCHA to submit Sudan inputs for GHO (2024) + projected number of people reached by the end of 2023 by clusters | HNO/HRP | OCHA |
| 7 November (TBC) | **STAKEHOLDER ENGAGEMENT**  Discuss   * PiN and severity analysis * HRP strategy, scope and parameters; strategic objectives * HPR target and financial requirements |  | OCHA, ICCG, HCT, INGO SC, Sub-national level |
| 1-16 November | * OCHA to draft the full HNRP | HNO/HRP | OCHA |
| 17-23 November | * OCHA to share the draft HNRP with clusters for review *(clusters will have one week for review)* | HNO/HRP | ICCG |
| 28 November – 4 December | * OCHA to share the update HNRP (in which Clusters’ feedback is reflected) with the HCT for review *(HCT will have one week for review)* | HNO/HRP | OCHA |
| 5 December | * [HCT] Seek final endorsement of the Sudan 2024 HNTRP | HNO/HRP | OCHA/HCT |
| 11 December | **Launch of 2024 Global Humanitarian Overview** (by the ERC and IASC Principals) | GHO | OCHA |
| 14 December (TBC) | **National launch of 2024 Sudan HRP** | HNO/HRP | OCHA |
| January 2024 | * Project Submissions | HRP | ICCG-partners |
| January 2024 | * Projects Review | HRP | OCHA, ICCG |