|  |  |  |  |
| --- | --- | --- | --- |
| ***Note: This timeline is tentative - Dates will change depending on developments related to the process.*** | | | |
| 31 January | ISNA TWG reflections | ISNA TWG | Completed |
| 07 February | ICCG After Action Review (AAR) for 2023 HPC process | OCHA | Completed |
| 06 March | Engagement with Food Security and Nutrition Monitoring System (FSNMS) secretariat | OCHA | Completed |
| 9 March | Development of the Inter-Sectoral Analytical Framework | OCHA/Cluster IMOs | Completed |
| 30 April | Endorsement of the Inter-Sectoral Analytical Framework | ICCG | Completed |
| 8 May | Clusters’ inputs to the Inter-Sector Needs Assessment (ISNA) tools | Clusters | Completed |
| 23 May | Review, update and endorsement of the ISNA data collection tools | ICCG | Completed |
| 6-7 June | Training of Trainers (ToT) training for data collection | ISNA TWG/Clusters | Completed |
| 12-16 June | Incorporating feedback from enumerators and updating the tool | ISNA TWG |  |
| 16 June | Field-level training of enumerators and piloting the tool | ISNA TWG/ State focal points |  |
| 12-26 June | Data analysis plan development and finalization | ISNA TWG/ Cluster IMOs |  |
| 19 June-04 Aug | ISNA field data collection (quantitative) | ISNA TWG |  |
| 19 June-04 Aug | ISNA field data collection (qualitative) | ISNA TWG |  |
| 30 June | Share draft HRP strategic and specific objectives with the ICCG | OCHA |  |
| 04 July | Inception workshop on scope of the humanitarian response, strategic and specific objectives, and plan for 2024-2026  (Suggest a full day ICCG+IMWG workshop) | OCHA | * Discuss the 2024-26 HRP scope and parameters. * Discuss the overall strategic and specific objectives. * Discuss and agree on a response monitoring framework, including intersectoral response indicators. * Share planning document template (combined HNO/HRP document) with clusters. * OCHA to share JIAF guidelines and methodology. * Present and discuss guidelines on project submission and costing methodology. * Discuss methodology for calculating humanitarian/nexus/solutions/development PiN * Calculation of cash PiN and target |
| 6 July | Share the updated strategic and specific objectives, response monitoring framework and costing methodology with ICCG for inputs | OCHA |  |
| 12 July | ICCG to share inputs to the strategic and specific objectives, response monitoring framework and costing methodology | ICCG |  |
| 18 July | Endorsement of the strategic and specific objectives, response monitoring framework and costing methodology by the ICCG | ICCG |  |
| 20 July | Endorsement of the strategic, specific objectives, response monitoring framework and costing methodology by the HCT | HCT |  |
| 1 August | Training on Response Planning and Monitoring (RPM) and Project Module for clusters | OCHA | Participants to include cluster coordinators and IMOs |
| 05-30 August | ISNA data cleaning and analysis | ISNA TWG |  |
| 31 August | Sharing of output tables and datasets with clusters | ISNA TWG | ISNA clean dataset shared with Cluster IMOs for sectoral analysis |
| 14 September | Submission of draft sectoral PiN, severity mapping and targets | Clusters | Clusters share draft sectoral PiN severity maps and targets in preparation for the Intersectoral Joint Analysis workshop. |
| 19 September | OCHA to present the draft PiN, severity mapping and targets to national and state-level ICCGs | OCHA |  |
| 21-22 September | Joint Inter-sectoral Analysis workshop | National and State-level ICCGs/IMWG/ISNA TWG/Context experts | Validate the intersectoral severity mapping, PiN and targets, funding requirements |
| 26 September | Present draft PiN, severity and targets to ICCG for endorsement over email | OCHA/ICCG | Endorsement of the sectoral and intersectoral analysis – severity, PiN and targets |
| 28 September | Present draft severity, PiN, target and financial requirements to HCT for endorsement | OCHA/HCT | Agreement/endorsement of the sectoral and intersectoral analysis - severity, PiN, targets and financial requirements |
| 03 October | Submission of cluster narrative inputs for the planning document (combined HNO/HRP) | Cluster coordinators | Clusters to share their inputs to the template provided by OCHA |
| 03 October | Finalize populating the RPM | Cluster IMOs | Cluster IMOs to finalize uploading cluster targets by indicators |
| 5 October | Project module training for cluster partners | OCHA | The training is for clusters and partners. |
| TBC | Opening of project module for project submission | OCHA |  |
| TBC | Clusters’ review and submission of project proposals through the HPC project module  1. Project review by partner organization  2. Project review and approval by clusters | Partners  Clusters  OCHA  HC | * Partners submit HRP projects. * Clusters review and approve projects   The hard deadline for finalizing, submitting and approving projects is on **31 October.** |
| 09-13 October (any day of the week) | Consultative meeting with Government on the draft 2024 PiN, severity, targets and financial requirements | HC/ OCHA | HC briefs Government on HRP process and present PiN, targets and financial requirements |
| 1 November | GHO submission with final PiN | OCHA |  |
| 03 November | Submission of draft Planning Document to ICCG for their comments | OCHA |  |
| 10 November | ICCG shares their inputs with OCHA | ICCG |  |
| 15 November | Share draft Planning Document with the HCT/ICCG for inputs | OCHA |  |
| 20 November | Endorsement of the Planning Document | ICCG/HCT |  |
| **22 November** | **Launch of the 2024 Planning Document** | Government /HC/OCHA/HCT/ICCG/Donors | OCHA to organize event and media/social media strategy |